## Instructions
Project Intake Form
TRANSMISSION ■
Analytics & Modeling • complete one workbook per project before kickoff
HOW TO USE THIS WORKBOOK
1 | Start on the PIF tab. Fill in every field with your project's details before any data work begins.
2 | Sample entries are shown in grey italic throughout the workbook — they're a worked example (an automotive “Probability To Buy” model). Type over them with your own information.
3 | Work left to right through the tabs: define the project (PIF), list your data (Data Source & Tables), plan the work (Detailed Timelines), then record the approach (Methodology, Algorithm).
4 | Keep the Definitions and Steps Docs tabs updated so anyone picking up the project can follow it.
WHAT'S IN EACH TAB
PIF | The core intake form — client, objective, analytics method, dependent variable, universe, backtest, deliverables and more.
Data Source & Tables | Every data source the project draws on: platform, source, table, location and access owner.
Detailed Timelines | Project plan by phase — task, owner, start/end dates and status.
Methodology | The stepwise modeling approach, with a notes column for project-specific decisions.
Algorithm | The technical model specification — model family, target, features, validation and scoring.
Definitions | Shared glossary of metrics and modeling terms.
Steps Docs | Checklist of supporting documents produced during the project.

## PIF
Project Intake Form
Sample entries shown in grey italic — replace with your project's details.
TRANSMISSION ■
1 PROJECT DETAILS
Client Contact | Internal — Transmission's own IP. No client yet, using dummy Marketo data. Real client plugs in later.
Transmission Contact | Swati Kumawat — building it Jonathan Cocek — sponsor
Project Name | Email Nurture Segmentation (EASE) — Transmission Model
Transmission Project # | [project # — TBD]
Date Submitted | 6/25/2026
Priority | High
Target Completion Date | 7/13/2026
2 BUSINESS PROBLEM & OBJECTIVE
Objective | Sort every contact into a behaviour group (Rising Star, MVP, Hand Raiser, Question Mark, Napper, Dormant) from how they open, click and how recently. Build once on dummy data, reuse for any client.
Primary & Secondary KPIs | Everyone lands in a group, no one missed. Groups make sense — higher groups open/click more. Watch lift per group + contacts moving up over time.
3 ANALYTICS SPECIFICATION
Analytics Method | Use old EASE logic as the guide, rebuild in Python. Per contact: count sends/opens/clicks over time, work out rates + recency + tenure + trend, combine (multi-factor) into a group. Phase 1 rules, Phase 2 maybe clustering.
Unit of Analysis | One contact = one email. One row per contact, per scoring date.
Dependent Variable Specification | None — not a predict-a-number model. Output = the group + a confidence score.
Analysis Universe | Emailable contacts (not unsubscribed) with 1+ email in last 24 mo (~20k of 122k). TBD: drop never-emailed or keep as a 'no data' group.
Snapshot / Cut-off Date | Score at a point in time (dashboard uses 28 May 2026), look back 24 mo. Re-run monthly. Dates relative — nothing hardcoded.
Backtest | Check group sizes + that open/click climb right. Match the dashboard's 6 groups. Movement month to month should be steady.
4 DELIVERY & NOTES
Deliverables | 1. Python code in the repo (no hardcoded creds/dates). 2. Output in the dashboard's shape. 3. This workbook. 4. Short plain-English write-up.
Additional Considerations | 2 data gaps + fixes: no sign-up date -> use first activity; no bounce -> not-unsubscribed = reachable. Casino bits dropped; add pipeline/lead score for real clients later. Re-tune old cut-offs for B2B. Check w/ Jonathan: replace dashboard data, or match it?

## Data Source & Tables
Data Sources & Tables
List every data source the project draws on, at the grain and history the analysis needs.
TRANSMISSION ■
Platform | Source | Table / View Name | Location / Schema | Credentials / Access Owner
Snowflake | Marketo contacts | ES_LEADS | MODEL_DEV / RAW_MKTO | S. Kumawat (key-pair)
Snowflake | Activity events | ES_ACTIVITIES | MODEL_DEV / RAW_MKTO | S. Kumawat
Snowflake | Email assets | ES_EMAIL_ASSETS | MODEL_DEV / RAW_MKTO | S. Kumawat
Snowflake | Scored output | ES_CONTACT_SEGMENTS | MODEL_DEV / RAW_MKTO | written by the algo
Snowflake | Seed originals (read-only) | LEADS_RAW / ACTIVITIES_RAW / EMAIL_ASSETS_RAW | MODEL_DEV / RAW_MKTO | platform team — don't touch
Marketo Engage (future) | Live feed at client go-live | REST / Bulk Extract | client tenant | client marketing ops
Tip: confirm every source joins to the unit of analysis (LEAD_ID) before the build.

## Detailed Timelines
Detailed Timelines
Plan the work by phase. Update status as the project progresses.
TRANSMISSION ■
Phase | Task | Owner | Start | End | Status
Kickoff & scoping | PIF sign-off, confirm data access | S. Kumawat / J. Cocek | 6/25/2026 | 6/26/2026 | In progress
Data setup | Clone + enrich ES_ tables | S. Kumawat | 6/29/2026 | 6/30/2026 | Not started
Python logic v1 | First working cut — for Jonathan to see code | S. Kumawat | 7/1/2026 | 7/3/2026 | Not started
Logic refine | Multi-factor rules + confidence | S. Kumawat | 7/6/2026 | 7/7/2026 | Not started
Full build | Score all contacts -> ES_CONTACT_SEGMENTS | S. Kumawat | 7/8/2026 | 7/9/2026 | Not started
Validation | Sizes, gradient, movement | S. Kumawat | 7/9/2026 | 7/10/2026 | Not started
Dashboard + delivery | New page + repo + write-up | S. Kumawat | 7/10/2026 | 7/13/2026 | Not started
Status: Not started / In progress / Complete / On hold. Weekdays only. 1-8 Jul = slower, not a stop. Final delivery 13 Jul.

## Methodology
Modeling Methodology
The stepwise approach, in order. The notes column records project-specific decisions.
TRANSMISSION ■
# | Step | What happens | Notes for this project
1 | Define the problem | Agree the segmentation goal and the groups | Sort nurtured contacts into 6 behavioural groups; output = group + confidence (no predicted target).
2 | Evaluate data sources | Inventory sources; confirm access and grain | RAW_MKTO ES_ tables (leads, activities, assets). Grain = contact.
3 | Specify features & universe | Define population and engagement features | Emailable, 1+ email in 24mo (~20k). Features: recency, frequency, tenure, trend, rates, lead score.
4 | Exploratory data analysis | Profile engagement; check distributions | ~32% open, ~10% click. Check group sizes look sensible.
5 | Treat variables | Handle missing values and outliers | No sign-up date -> first activity; no bounce -> not-unsub; cap velocity outliers.
6 | Choose segmentation approach | Pick the method | Phase 1 rules-based (RFM + trend), interpretable. Phase 2 optional k-means clustering.
7 | Define segment rules & thresholds | Set the multi-factor cut-offs | Recency bands + click depth + trend (recent vs prior) decide the group.
8 | Assign segments + confidence | Score every contact into one group | Each contact gets a group, a confidence score and a marketing/sales playbook.
9 | Profile the segments | Check each group makes sense | Confirm open/click rates step cleanly across groups (engagement gradient).
10 | Test stability | Check groups hold over time | Group sizes and month-to-month movement should be steady.
11 | Deploy | Productionise and refresh | Write ES_CONTACT_SEGMENTS; monthly re-score; feed the dashboard.
This is the default path. If a project skips or reshapes a step, record the reason in the notes column.

## Algorithm
Algorithm Specification
The technical model specification for this project.
TRANSMISSION ■
Item | Specification
Model family | Phase 1 — rules (RFM + trend). Phase 2 (maybe) — k-means.
Target (dependent variable) | None. Output = group (6) + confidence (0-1).
Unit of analysis | Contact (LEAD_ID) per score date.
Sampling design | Point-in-time, trailing 24 mo.
Candidate features | Sends/opens/clicks, rates, recency, velocity, tenure, trend, lead score.
Variable selection | Match dashboard groups; tune cut-offs to the data (re-tuned from casino).
Validation metrics | 100% coverage; open/click rates step cleanly across groups; steady month-to-month movement; group sizes sanity-checked.
Backtest window | Re-score prior month, compare. Ref dashboard 28 May 2026.
Scoring output | Group, label, confidence, features, playbook -> ES_CONTACT_SEGMENTS.
Refresh cadence | Monthly re-score; quarterly cut-off review.
Record any deviation from these settings, with the rationale, so the model is reproducible.

## Definitions
Definitions
Shared glossary of metrics and modeling terms. Add any term that isn't listed.
TRANSMISSION ■
Term | Description
Dependent variable | The outcome the model predicts (here: probability of an extra service in 45 days)
Independent variable | A predictor / feature used to estimate the outcome
Analysis universe | The set of records in scope for the model, with inclusion / exclusion rules
Snapshot | A point-in-time view of each record; here, eight 45-day windows are stacked
Backtest | Validating the final model on a later, unseen time period
PSI | Population Stability Index — measures drift in score / input distributions over time
Imputation | Filling missing values using a defined, repeatable rule
CTR | Click-through rate = clicks / impressions
Impressions | Count of times an ad is shown to a prospect
Open rate | Opens / sends
Click rate | Clicks / sends
Click-to-open (CTOR) | Clicks / opens
Recency | Days since last open/click
Tenure | Months since first activity (sign-up proxy)
Engagement velocity | Sends per active month
Behavioural segment | The group a contact falls in (Rising Star, MVP, Hand Raiser, Question Mark, Napper, Dormant)
Confidence | How well a contact fits its group (0-1)
Reactivation | Bringing a dormant contact back to engaged
Lead score | 0-100 engagement/intent score per contact

## Steps Docs
Supporting Documents
Checklist of documents produced during the project. Add links as each is completed.
TRANSMISSION ■
SN | Document | Detail / Link
1 | Data dictionary | ES_ tables & columns
2 | Data profile / EDA | Email_Segmentation_Roadmap_and_Data.md
3 | Dashboard framework | Dashboard_Framework_Email_Segmentation.md
4 | Logic design | Multi-factor rules + confidence
5 | Scoring code | Python engine in TransmissionCDP repo
6 | QC log | Sizes, gradient, movement checks
7 | New dashboard page | Wired to ES_CONTACT_SEGMENTS
8 | Final write-up | Plain-English methodology